## README
05 90-Day Execution Plan - DICEUS SEO & AI Search
PURPOSE: the strategy converted into sequenced, owned, testable work.
CLASSES: MUST DO = protects equity or unblocks everything else ¦ HIGH-VALUE NEXT = strong evidence, start once dependencies clear ¦ LATER / VALIDATE FIRST = blocked on data (GSC/GA4/CRM/product decisions).
WAVES: Days 1-30 fix, baseline, decide ¦ Days 31-60 reposition & build ¦ Days 61-90 validate, consolidate, scale.
GOVERNANCE: every destructive change (redirect, consolidate, deindex, retitle a ranking page) requires a GSC baseline + change-log entry + 14-day post-change check + rollback plan.
SHEETS: Plan ¦ By_Wave ¦ Workstream_DoD ¦ KPIs ¦ Top5_Priorities ¦ Not_Yet ¦ Roles

## Plan
id | wave | workstream | task | class | owner | depends_on | start_day | end_day | definition_of_done | status
W1-01 | Days 1-30 | Measurement | Get GSC (domain property), GA4, CRM landing-page lead export; snapshot 16-month baselines per URL & query | MUST DO | SEO lead + Marketing ops | - | 1 | 7 | Baseline sheet per URL: clicks, impressions, avg pos, leads; stored in BigQuery/Sheets | Not started
W1-02 | Days 1-30 | Technical | Remove stray noindex,nofollow on 3 product pages; re-submit sitemap; URL Inspection | MUST DO | WP developer | - | 1 | 5 | Raw HTML shows only 1 robots meta, no noindex; GSC 'URL is on Google' for all 3 | Not started
W1-03 | Days 1-30 | Technical | Template audit: find source of hard-coded robots meta (theme/ACF field) and add CI check that fails deploy if a sitemap URL has noindex | MUST DO | WP developer + SEO | W1-02 | 1 | 10 | Automated check runs on every deploy; alert to Slack | Not started
W1-04 | Days 1-30 | Technical | Staging hygiene: likeprod.diceus.com removals in GSC, X-Robots-Tag noindex on all non-prod hosts | MUST DO | DevOps | W1-01 | 1 | 10 | 0 staging URLs in site: search; GSC removal approved | Not started
W1-06 | Days 1-30 | Architecture | Decision workshop: product catalogue truth table (which products are sellable SKUs, which are modules/accelerators) | MUST DO | CEO/Product + SEO | - | 5 | 15 | Signed-off list; drives which pages are 'product' vs 'capability' | Not started
W1-09 | Days 1-30 | AI Search | Prompt panel v2: 40 prompts x 3 runs x (Claude, ChatGPT, Perplexity, Google AI Overviews/AI Mode) baseline | MUST DO | SEO/AI automation | - | 5 | 20 | Baseline SoV table + cited-source list stored; rerunnable script | Not started
W1-11 | Days 1-30 | Authority | Rename directory listings to 'DICEUS <Product>'; claim/complete US Capterra, G2, Gartner PI; start review program with existing clients | MUST DO | Marketing | - | 5 | 30 | All listings branded; review requests sent to >=15 clients | Not started
W1-13 | Days 1-30 | Proof | Alt-risk proof sprint: secure 1-3 captive/RRG/MGA references; write 2-3 case studies (anonymised fallback) | MUST DO | CEO/Sales + writer | - | 5 | 45 | >=2 alt-risk case studies live and linked from captive/RRG pages | Not started
W1-05 | Days 1-30 | Technical | Legacy redirects: fix 404s/chains from Wayback inventory that have backlinks | MUST DO | SEO + developer | W1-01 (links data) | 10 | 30 | All legacy URLs with >=1 referring domain resolve in 1 hop to a relevant 200 | Not started
W1-07 | Days 1-30 | Architecture | Query-ownership map v1: one owner URL per cluster (from 03 clusters + GSC) | MUST DO | SEO lead | W1-01, W1-06 | 10 | 25 | Every priority cluster has exactly one owner URL; conflicts listed | Not started
W1-08 | Days 1-30 | Content | Captive Management Platform page rebuild per spec (Appendix A of 04) | MUST DO | Product marketer + SEO + designer | W1-02, W1-06 | 10 | 30 | Spec acceptance criteria all met | Not started
W1-10 | Days 1-30 | AI Search | Schema: Organization (sameAs, description as insurance software vendor), SoftwareApplication on product pages, FAQPage where visible FAQ exists; expand llms.txt | MUST DO | Developer + SEO | W1-06 | 10 | 30 | Rich Results Test passes on all product templates; llms.txt lists every product .md | Not started
W1-12 | Days 1-30 | Technical | Product-template performance: confirm with CrUX/RUM; load consent banner without delaying LCP (preload/inline CSS, async config); collapse http://www 2-hop redirect to 1 hop | HIGH-VALUE NEXT | WP developer | W1-01 | 10 | 30 | Mobile LCP < 2.5 s (p75 field, or lab median of 3) on product template; http://www -> https://diceus.com in 1 hop | Not started
W2-01 | Days 31-60 | Architecture | Homepage step 1: strengthen /services/custom-software-development/ as owner of generic dev queries (title, internal links from services hub) | MUST DO | SEO | W1-01 (GSC gate) | 31 | 40 | Owner page live; internal links updated | Not started
W2-03 | Days 31-60 | Architecture | Navigation v2: Products ¦ Alternative Risk ¦ Solutions by segment ¦ Services ¦ Resources; generic services collapsed under Services hub | MUST DO | UX + dev + SEO | W1-06, W1-07 | 31 | 55 | Template links per page reduced from ~300 to <=120; products in first menu column | Not started
W2-04 | Days 31-60 | Content | Alternative Risk hub (AROP) expansion + segment page Self-insured groups & pools (captive managers -> captive mgmt page; RRGs -> RRG product page) | MUST DO | Product marketer + writer + SEO | W1-06, W1-08 | 31 | 60 | Hub + new segment page live, hub<->spoke links to all 6 alt-risk pages, each with proof block | Not started
W2-05 | Days 31-60 | Internal links | Contextual links: 86 insurance posts + 18 insurance services -> owner product pages (scripted suggestions, human approval) | MUST DO | SEO + editor | W1-07 | 31 | 50 | Median contextual inlinks to products >= 60 (from 24) | Not started
W2-08 | Days 31-60 | Authority | Trade press: pitch VCIA case/insight piece to Captive Review / Captive International / Carrier Management | HIGH-VALUE NEXT | PR/CEO | Named customer (if available) | 31 | 60 | >=1 earned article with link to alt-risk hub | Not started
W2-09 | Days 31-60 | AI Search | Entity: Wikidata item (notability-safe, factual), consistent descriptions across Clutch/Crunchbase/LinkedIn as 'insurance software vendor + services' | HIGH-VALUE NEXT | Marketing + SEO | - | 31 | 45 | Wikidata item live with refs; profiles updated | Not started
W2-10 | Days 31-60 | Automation | Weekly pipeline: crawl diff + GSC pull + rank/AI-panel rerun + anomaly alerts (see 06 §L) | HIGH-VALUE NEXT | SEO automation | W1-01, W1-09 | 31 | 60 | Runs unattended weekly; Slack digest | Not started
W2-11 | Days 31-60 | Content | /trust/ (security, hosting, data ownership, cert status) and /pricing/ (model, drivers, implementation range) pages | MUST DO | Product + SEO + legal | W1-06 | 31 | 50 | Both live, linked from all product pages; claims verified by legal | Not started
W2-02 | Days 31-60 | Architecture | Homepage step 2: new title/H1/hero/sections per 04 §4.4 (products-first), keep a services strip | MUST DO | SEO + design + dev | W2-01 | 40 | 50 | Live; GSC monitored daily for 14 days; rollback plan documented | Not started
W2-07 | Days 31-60 | Content | PAS page: segment H2s + FAQs for captives/MGAs/RRGs; modernization guide links | HIGH-VALUE NEXT | SEO + writer | W1-07 | 40 | 60 | Page owns 'PAS for MGAs/captives' variants; FAQ schema valid | Not started
W2-12 | Days 31-60 | Content | Captive Management Software RFP template + RRG Buyer's Guide (ungated HTML + PDF) | HIGH-VALUE NEXT | Product marketer + SME | W1-06 | 40 | 60 | Both live under AROP hub; pitched to VCIA / captive trade media | Not started
W2-06 | Days 31-60 | Content | Comparison page: Origami Risk alternatives for captive managers (fact-checked, fair) | HIGH-VALUE NEXT | Writer + product | W1-06 | 45 | 60 | Live, legal-reviewed, cites public sources | Not started
W3-01 | Days 61-90 | Content | Segment page: MGAs & program administrators | HIGH-VALUE NEXT | Writer + SEO | W1-06 | 61 | 80 | Live + linked from PAS/UW/AROP | Not started
W3-02 | Days 61-90 | Architecture | Insurance services overlap consolidation (policy-admin/policy-mgmt, claims/health-claims, portal/customer-portal) - only pairs proven to cannibalize in GSC | LATER / VALIDATE FIRST | SEO + dev | W1-01, W1-07 | 61 | 80 | 301s live, 0 chains, survivor gained impressions within 6 weeks | Not started
W3-04 | Days 61-90 | Content | Claims Management product page (only if W1-06 confirms standalone product) | LATER / VALIDATE FIRST | Product marketer | W1-06 | 61 | 90 | Live or explicitly declined | Not started
W3-05 | Days 61-90 | Content | Feature pages: bordereaux management, captive/cell accounting, statutory filing tracker (only clusters with validated demand) | LATER / VALIDATE FIRST | Writer + SEO | Ahrefs/GSC demand check | 61 | 90 | Built only where demand confirmed | Not started
W3-06 | Days 61-90 | Technical | Case-study filter archives -> noindex,follow (if 0 organic entrances) | LATER / VALIDATE FIRST | Developer | W1-01 | 61 | 75 | Archives noindexed; sitemap cleaned | Not started
W3-03 | Days 61-90 | Architecture | Generic services: consolidate exact duplicates proven by GSC; leave rest | LATER / VALIDATE FIRST | SEO + dev | W1-01 | 65 | 85 | Only zero-value or duplicate URLs touched; change log kept | Not started
W3-07 | Days 61-90 | Measurement | Day-90 review: impressions/clicks per cluster, product-page leads, AI SoV vs baseline; re-prioritize | MUST DO | SEO lead | All | 85 | 90 | Review deck + updated backlog | Not started

## By_Wave
wave | HIGH-VALUE NEXT | LATER / VALIDATE FIRST | MUST DO
Days 1-30 | 1 | 0 | 12
Days 31-60 | 6 | 0 | 6
Days 61-90 | 1 | 5 | 1

## Workstream_DoD
workstream | definition_of_done
Technical | 0 sitemap URLs with noindex; deploy guardrail live; staging de-indexed; legacy URLs with links resolve in 1 hop; no internal links to redirects
Architecture | Query-ownership map signed off; nav v2 live with products first and <=120 template links; homepage repositioned with no unexplained >20% non-brand click loss after 28 days
Content | Captive page per spec; alt-risk hub + 3 segment pages live with proof; each page indexed and has >=10 contextual inlinks
Internal links | Median contextual inlinks to product pages >= 60 (baseline 24); every insurance post links to its owner product
AI Search | Panel v2 baseline across 4 engines; schema valid on all product templates; Wikidata live; listings branded; SoV tracked monthly
Authority | >=15 review requests sent, >=5 published reviews on US listings; >=1 earned trade-press article
Measurement | GSC/GA4/CRM baselines stored; weekly automated digest; day-90 review delivered
Automation | Weekly crawl diff + GSC pull + AI panel run unattended; alerts on noindex/status/title changes for priority URLs

## KPIs
KPI | source | baseline | 90-day target | cadence
Indexed priority product URLs | GSC URL Inspection / Pages report | 3 of 23 noindexed (FACT) | 23/23 indexed by day 14 | weekly
Non-brand impressions - alt-risk cluster | GSC (query regex) | DATA UNAVAILABLE | baseline +50% by day 90 (set after baseline) | weekly
Non-brand clicks to product pages | GSC (page filter /insurance/solutions/) | DATA UNAVAILABLE | trend up vs baseline; no loss on owners | weekly
Demo requests from organic landing on products | GA4 + CRM | DATA UNAVAILABLE | baseline then +25% | monthly
Median contextual inlinks to products | Own crawler | 24 (FACT) | >= 60 | monthly
AI share of voice - unbranded prompts | Prompt panel v2 (4 engines x 3 runs) | Claude: 2/16 (FACT) | Claude >= 5/16; establish others | monthly
Branded entity answer correct ('What is DICEUS?') | Prompt panel | Fail (FACT) | Pass on >= 3 of 4 engines | monthly
Published reviews on US product listings | G2 / Capterra / Gartner PI | 0 (FACT) | >= 5 | monthly
Generic-service clicks (guardrail) | GSC | DATA UNAVAILABLE | no unexplained drop > 20% | weekly

## Top5_Priorities
decision | evidence | expected_impact | rationale | dependency_or_risk
1. Restore indexation of the alternative-risk product pages (and add a guardrail so it can't recur) | FACT: 3 sitemap URLs carry a 2nd hard-coded <meta robots='noindex, nofollow'> (verified in raw HTML on 2026-10-06). Two of them (Captive Management Platform, RRG Platform) are the pages that won 100% of DICEUS's unbranded AI-answer mentions and hold #1 for 'risk retention group software' in our SERP sample. | Protects the only territory where DICEUS already wins; prevents silent de-indexing of the strategic growth line. | Zero-cost, zero-risk fix with asymmetric upside. Done first because every other alt-risk investment depends on these pages being indexable. | Dependency: WordPress template/ACF access. Risk: the noindex may be intentional (e.g. unreleased page) -> confirm with product owner in 24h.
2. Make Alternative Risk the first fully built product cluster (hub + segment pages + proof) | FACT: diceus.com #1 for 'captive insurance software', 'risk retention group software', 'alternative risk management software' (SERP proxy); competing SERPs are thin; VCIA partnership (Jun 2026); 262 US RRGs / 40 US captive domiciles. INF: most winnable commercial territory. | Highest ratio of commercial value to SEO difficulty; aligned with the strategic growth bet. | Feasibility 5/5 and relevance 5/5 - the only territory scoring top on both. | Dependency: product truth table (what is sellable) + at least one referenceable customer. Risk: niche demand volume is unverified (DATA UNAVAILABLE).
3. Reposition the Homepage from 'custom software development company' to an insurance-software product company - in two GSC-gated steps | FACT: homepage title/H1 = 'Custom software development company'; title-similarity 0.99 with /services/custom-software-development/; brand SERP surfaces services pages; AI answer quoted '$25-49/hr' as PAS pricing. | Aligns the site's strongest page and the entity description with the product strategy; resolves homepage cannibalization. | The homepage is the main input to how search engines and LLMs classify DICEUS. | Risk: HIGH if the homepage currently drives generic-dev leads. Mitigation: move generic intent to the services owner page first; monitor 14 days; rollback ready.
4. Re-weight internal architecture toward Products (nav + contextual links), without changing URLs | FACT: median contextual inlinks - products 24, insurance services 75, generic services 93; ~300 template links on every page; 190 generic service/industry/expertise URLs vs 23 product URLs. | Products become the strongest-linked commercial pages; clearer hierarchy for crawlers and LLMs. | Achieves the architecture change with near-zero equity risk: hierarchy via links and hubs, not URL migration. | Dependency: query-ownership map + nav design. Risk: demoting generic services could reduce their rankings -> monitor per-URL via GSC.
5. Build entity & third-party proof for AI search (branded listings, reviews, schema, Wikidata, analyst/trade inclusion) | FACT: 'What is DICEUS?' resolved to homonyms; 0 reviews on all product listings; listings surface without the brand; analyst lists/G2 source most category answers; 0/23 product pages have product schema; llms.txt lists 1 product. | Moves DICEUS from 2/16 to a measurable share of unbranded AI answers in priority categories. | AI answers are assembled from third-party sources DICEUS doesn't control - on-site work alone can't fix it. | Dependency: client cooperation for reviews. Risk: measurement noise (LLM non-determinism) -> 3 runs/prompt, track trends not points.

## Not_Yet
decision_not_executed_yet | what_is_unknown | why_acting_now_is_risky | evidence_needed
Prune / noindex / redirect the ~190 generic service, expertise and non-insurance industry pages | Their organic clicks, rankings, backlinks and lead contribution (DATA UNAVAILABLE: no GSC, GA4, CRM). | They may be today's main lead engine; services are 'commercially useful and real'. Blind pruning could destroy revenue and link equity. | 12-16 months GSC clicks/impressions per URL, GA4 conversions, CRM lead source by landing page, referring domains per URL.
Migrate product URLs to a new /products/ folder (or rename /insurance/solutions/) | Backlinks and directory/marketplace links per product URL; whether the folder name has any measurable ranking effect. | URL migration resets signals and risks equity loss (the site already shows legacy-migration debris); the hierarchy goal is achievable via nav, hubs and links. | Referring-domain data per URL (Ahrefs/GSC links), GSC performance baseline; evidence that the current path hurts CTR or understanding.
Merge the two captive product pages (captive-insurance-software vs captive-management-platform) or the overlapping insurance-service pairs | Which URL Google prefers per query, whether both rank for the same queries, and whether they are distinct SKUs. | One of them is currently #1; consolidating the wrong way could lose the best position in the strategic niche. | GSC query-by-page report (cannibalization check), product team confirmation of SKU boundaries, 4-6 weeks of post-split data.

## Roles
role | responsibilities
SEO & AI Search lead (this role) | Owns strategy, query-ownership map, measurement, AI panel, automation; approves every destructive change
WordPress developer | Templates, robots/schema, nav v2, redirects, deploy guardrails
Product marketing / product owners | Product truth table, features, proof, segment messaging
Content writer(s) + insurance SME | Segment pages, comparison page, refreshes; SME fact-check
Designer / UX | Homepage, nav, product page template
Marketing / PR | Listings, reviews, trade press, analyst relations
CEO / Head of Growth | Positioning sign-off (homepage), customer references